## Main
See | https://techformist.com/free-agile-scrum-excel-template
Scrum Project
Product | Parking Garage |  | Date | 9/20/21-10/1/21
Replit |  |  | Sprint # | 1
Team
Scrum Master | Rachel Grossbauer |  | Team # | 1
Developers | Joshua Bowman
Will Oberholtzer
Sean Sharo
Epic | [5 empty] | Sprint Plan |  | CS275 Garage
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks | Master
1 | Platforms / GUI / Data | 20/Sept/21 | 2021-10-01 | in progress |  | Spr. 1.1 | 2021-09-20 | 2021-10-01 | in progress | 4 | 1 | First user story completed, 3 to go unless we think of more | Rachel
2 | Daily Customer Functionality |  |  |  |  | Spr. 1.2 | 2021-10-04 | 2021-10-15 |  |  |  |  | Ian
3 | Long Term Client Functionality |  |  |  |  | Spr. 1.3 | 2021-10-18 | 2021-10-29 |  |  |  |  | Josh
4 | Municipality |  |  |  |  | Spr. 1.4 | 2021-11-01 | 2021-11-12 |  |  |  |  | Will
5 | Management |  |  |  |  | Spr. 1.5 | 2021-11-15 | 2021-11-26 |  |  |  |  | Josh
[6 empty] | Spr. 1.6 | 2021-11-29 | 2021-12-10 |  |  |  |  | Sean
Formulas:
CS275 Garage = [Start]+11
Start = [CS275 Garage, row above]+3

## Backlog
Backlog
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
1 |  | Scrum Master | Know what language to use | I can create a shared project | Everyone can edit the project | Completed, Replit created | Highest | Completed
2 |  | Scrum Master | Assign teammates things to get done | We can finish our goals on time | Talk with team and write things for each person to do in their excel spreadsheet | in progress | High
3 |  | Scrum Master | Determine how many classes we need in our project | I can better predict how large of a project we have to complete | Discuss with teammates the different classes we need and create them | in progress | Medium
4 |  | Developer | Figure out what we want our program to do | I can work on the project | Take some notes down with the team in our team meeting | in progress | Highest
5 |  | Developer | Know what data we are going to store about the customer | I can write the software that stores and access the data | List of information we're storing about client is complete
6 |  | Developer | Know what the format of the data is for the database | I can write code that puts data in the database and reads data from the database | Data has been written to and retrieved from database
7 |  | Developer | Use a system for configuration management | Work on a common development codebase without clobbering others work or introducing errors | CM system has been determined, developer has tried pulling commiting and pushing.
8 |  | Constant consumer | pay less often | I can always use parking garage | any one can
9 |  | Management | Check how many cars come into garage | I can keep track of how many spots are free in the parking garage | Data shows how many spots are available.
10 |  | Frequent Customer | reserve/have an individual spot | I can guarantee a spot is available | those who pay frequently and use often can have reserved spot

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 | 221 |  |  |  |  | 2 | -2 | 1 |  | 1
1.1 | 224 |  |  |  |  | 1 | -1 |  | 1
1.1 | 225 |  |  |  |  | 5 | -5 |  | 1 |  | 2 |  | 1 | 1
1.1 | 229 |  |  |  |  | 3 | -3 |  |  | 1 |  | 1 |  |  | 1
1.1 | 251 |  |  |  |  | 13 | -13 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.1 | 253 |  |  |  |  | 1 | -1 | [9 empty] | 1
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 0 | 25 | -25 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 2
|  |  |  | Burn down |  |  |  | -4 | -8 | -11 | -14 | -16 | -18 | -20 | -22 | -23 | -25
|  |  |  | Burn up |  |  |  | 4 | 8 | 11 | 14 | 16 | 18 | 20 | 22 | 23 | 25

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms