## Main
See | https://techformist.com/free-agile-scrum-excel-template
Scrum Project
Product | Parking Garage |  | Date | 10/04/21-10/15/21
Replit | https://github.com/rgrossbauer/Parking-Garage |  | Sprint # | 2
Team
Scrum Master | Ian Utz |  | Team # | 1
Developers | Joshua Bowman
Will Oberholtzer
Sean Sharo
Rachel Grossbauer
Epic | [5 empty] | Sprint Plan |  | CS275 Garage
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks | Master
1 | Platforms / GUI / Data | 20/Sept/21 | 2021-10-01 | Completed | Set up all necessary classes for our garage and worked on those classes all week | Spr. 1.1 | 2021-09-20 | 2021-10-01 | Completed | 5 | 5 | All user stories/goals completed | Rachel
2 | Daily Customer Functionality | 2021-10-04 | 2021-10-15 | Completed | Welcome Screen and Check In New Customer | Spr. 1.2 | 2021-10-04 | 2021-10-15 | Completed | 10 | 10 | Connected Kiosk to ParkingGarage successfully | Ian
3 | Long Term Client Functionality | 2021-11-01 | 2021-11-14 | Completed | Can now make sure a client can't check in twice and show available spots. | Spr. 1.3 | 2021-11-01 | 2021-11-14 | Completed | 5 | 5 | User stories completed | Josh
4 | Municipality |  |  |  |  | Spr. 1.4 | 2021-11-17 | 2021-11-28 |  |  |  |  | Will
5 | Management |  |  |  |  | Spr. 1.5 | 2021-12-01 | 2021-12-12 |  |  |  |  | Josh
[6 empty] | Spr. 1.6 | 2021-12-15 | 2021-12-26 |  |  |  |  | Sean
Formulas:
CS275 Garage = [Start]+11
Start = [CS275 Garage, row above]+3

## Backlog
Backlog
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
1 |  | Scrum Master | Know what language to use | I can create a shared project | Everyone can edit the project | Replit created | Highest | Completed
2 |  | Scrum Master | Assign teammates things to get done | We can finish our goals on time | Talk with team and write things for each person to do in their excel spreadsheet | Rachel will do as scrum master | High | Completed
3 |  | Scrum Master | Determine how many classes we need in our project | I can better predict how large of a project we have to complete | Discuss with teammates the different classes we need and create them | Everyone | Medium | Completed
4 |  | Developer | Figure out what we want our program to do | I can work on the project | Take some notes down with the team in our team meeting | Everyone | Low | Completed
5 |  | Developer | Write more user stories | I can base the program off of something | Add user stories to this document and check in with the scrum master when they are done | Josh and Will | Highest | Completed
6 |  | Developer | Know what the format of the data is for the database | I can write code that puts data in the database and reads data from the database | Data has been written to and retrieved from database
7 |  | Developer | Use a system for configuration management | Work on a common development codebase without clobbering others work or introducing errors | CM system has been determined, developer has tried pulling commiting and pushing.
8 |  | Constant consumer | pay less often | I can always use parking garage | any one can
9 |  | Management | Check how many cars come into garage | I can keep track of how many spots are free in the parking garage | Data shows how many spots are available. | Ian | High | Completed
10 |  | Frequent Customer | reserve/have an individual spot | I can guarantee a spot is available | those who pay frequently and use often can have reserved spot
11 |  | Manager | be able to know where a certain vehicle is | management can keep track of all the vehicles in the lot | if a vehicle is in a spot, there should be a directory to tell which spot |  | High
12 |  | Disabled customer | Have handicap parking | Spots can be handicap accessible | Elements in array are reserved for disabled people | Ian and Josh | Medium | Completed
13 |  | Consumer | know how busy the lot is | I do not search for hours | Tracker of spots available | Sean | Medium
14 |  | Developer | maximize each class | code is crisp and takes less computing | Anything that makes Classes more concise | Sean | Medium
15 |  | Customer | Know the time that I clock in and out | I am charged the correct amount | Put in the check in time and check out time for each customer | Sean | Medium | Completed
16 |  | Customer | Have a welcome screen | I know prices before entering parking garage | Instantiate the Kiosk class and have it be an instance in the main | Rachel | High | Completed
17 |  | Customer | Know where the handicap spots are | I can easily access them | Build prebuilt handicap spots for every floor | Josh | Medium | Completed
18 |  | Developer | Differentiate different types of customers | I can proces their payments correctly | In main, use an if else function to path a difference between new and existing customers | Everyone | High | Moving to Sprint 3
19 |  | Manager | Have the kiosk collect payments | I can receive a payment each time someone enters the garage | Create a scanner in the kiosk that collects money | Rachel | Medium | Completed
20 |  | Developer | Have a way to leave garage | we can make parking spots empty in our memory | If a license is entered into kiosk and it is in the ParkingSpot array then take it out | Sean | Medium | Completed
21 |  | Customer | See the available spots in the garage | I can map where to park my car | Show a display of the Garage in a 2D format | Ian | High | Completed
22 |  | Management | Make sure the data stays updated | Customers can see what is happening and what is available in real time | Show the flat file database to consistenly update and not restart after every rerun | Ian | Highest | Completed
23 |  | management | Track and update customer's balance | customers can enter quickly as long as funds are present | update balance for each use by repeat customer in ParkingGarage | Will | High | In Progress

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 | 221 | Sprint 1 | Rachel | Completed | 5 | 5 | 0 | 1 |  | 1 |  | 1 | 1 |  | 1
1.1 | 224 | Sprint 2 | Ian | In progress | 10 | 10 | 0 | 1 | 2 |  | 2 | 1 |  | 1 | 1 | 1 | 1
1.1 | 225 | Sprint 3 | Josh |  |  | 0 | 0
1.1 | 229 | Sprint 4 | Will |  |  | 0 | 0
1.1 | 251 | Sprint 5 | Josh |  |  | 0 | 0
1.1 | 253 | Sprint 6 | Sean |  |  | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 15 | 15 | 0 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 1
|  |  |  | Burn down |  |  |  | 13 | 11 | 10 | 8 | 6 | 5 | 4 | 2 | 1 | 0
|  |  |  | Burn up |  |  |  | 2 | 4 | 5 | 7 | 9 | 10 | 11 | 13 | 14 | 15

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks
1 | 2021-09-22 | Rachel | Discussing what features we want in our program | Start writing the actual code
| 2021-10-01 | Rachel | Finish up being scrum master | Pass off the job to Ian | Being scrum master
2 | 2021-10-04 | Ian | Finshing up the classes | Checking in a new customer
| 2021-10-15 | Ian | Check In a New Customer | Discussing checking for returning customers | Being Scrum master

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms

## Rachel
Assignments for the Week (Sprint 1)
Everyone will work on user story 4
Monitor everyone and make sure they get their tasks done
Keep updating this google sheet
Run the Thursday meeting
Assignments for the week (Sprint 2)
Work on the Kiosk Class to instantiate it into the main
All work together on checking a new customer into the parking garage array and finalizing the check in process for a new customer
Assignments for the week (Sprint 3)

## Josh
Assignments for the Week (Sprint 1)
Think about user story #4
User story #5
Assignments for the week (Sprint 2)
Work on the ParkingSpot class to set certain spots to be handicap
All work together on checking a new customer into the parking garage array and finalizing the check in process for a new customer
Assignments for the week (Sprint 3)

## Sean
Assignments for the Week (Sprint 1)
Think about user story #4
User story #3
Assignments for the week (Sprint 2)
Work on putting in the calender class into the main
All work together on checking a new customer into the parking garage array and finalizing the check in process for a new customer
Assignments for the week (Sprint 3)

## Will
Assignments for the Week (Sprint 1)
Think about user story #4
User story #5
Assignments for the week (Sprint 2)
Finish out payment whenever a new customer enters the parking garage
All work together on checking a new customer into the parking garage array and finalizing the check in process for a new customer
Assignments for the week (Sprint 3)

## Ian
Assignments for the Week (Sprint 1)
Think about user story #4
User story #3
Assignments for the week (Sprint 2)
Helping Josh with setting certain handicap spots
All work together on checking a new customer into the parking garage array and finalizing the check in process for a new customer
Assignments for the week (Sprint 3)